## Cover Sheet
Document Number: | CF-8-ALL-4800 | Document Title: | APQP Checklist
Document Usage: | Supplier APQP Process | Document Scope: | Corporate / All Regions
Supplier Advance Product Quality Planning - APQP
Company |  | Part Number
Description
Address |  | Drawing
Revision
P.O. Number
Customer Plant(s) |  | Date Submitted
Submitted By
Title
Comments

## Milestone 1
Milestone #1- "Supplier Kick Off/ Plan and Define the Program"
Minor Milestone | Minor Milestone Description | Detail | Detail Description | Supplier Plan | Due Date | Date Completed | Evidence Available Y/N
1.1 | Identify TI Fluid Systems and supplier team contacts/role/responsibilities and contact information | 1.1.1 | Program managers- Who will be representing Program Management on this Team? Names?
|  | 1.1.2 | Product Engineers- Who will be representing Engineering on this Team? Names?
|  | 1.1.3 | Manufacturing Engineers- Who will be representing Manufacturing Engineering on this team? Names?
|  | 1.1.4 | Quality- Who will be representing Quality on this Team? Names?
|  | 1.1.5 | Logistics / Material Handling- Who will be representing Logistics/Material Handling on this team? Names?
|  | 1.1.6 | Purchasing- Who will be representing Purchasing on this Team? Names?
1.2 | Define key supplier metrics and communicate within both organizations / quality and reliability goals. | 1.2.1 | Quality Targets (Launch and Production) Set KPI metrics and expectations for quality and reliability.
|  | 1.2.2 | Delivery Targets (Launch and Production) Set delivery expectations- Which is 100% on-time unless agreed upon by TI Fluid Systems.
|  | 1.2.3 | Warranty / Reliability targets Set Warranty and Reliability targets as agreed upon with TI Fluid Systems
|  | 1.2.4 | Determine PPAP submission level / Requirements as agreed upon with TI Fluid Systems
|  | 1.2.5 | Validation plan / DVP&R- Establish DVP&R plan/proposed timing with TI Fluid Systems.
|  | 1.2.6 | APQP meeting schedule / Milestone review dates- Determine APQP meeting and follow up dates.
1.3 | Initial supplier program plan and timing / Target dates | 1.3.1 | Start of Production (SOP)
|  | 1.3.2 | Preliminary Ramp Plans / Bank requirements- define TIFS requirements and how supplier will support them.
|  | 1.3.3 | PPAP due date
|  | 1.3.4 | Prototype / sample due date(s)
|  | 1.3.5 | Capital and equipment timing- Proposed timing for key decision making and release requirements to ensure capital equipment is available on time.
|  | 1.3.6 | Production trials / PSO/ Run at Rate- define dates and requirements for Production trials and PSO
|  | 1.3.7 | Lot Control/ Traceability- define how lot size will be determined, where lot control will be applied and response time to ensure plan will meet TIFS and OEM customer requirements. define tracking scheme, labeling and response process.
1.4 | Conduct cross functional design review / Fit, form, function, and S&C discussion | 1.4.1 | Drawing release- Agreed upon date when drawing will be released and made available.
|  | 1.4.2 | Review design intent, functional requirements and Significant and Critical features from TIFS and supplier perspective.
|  | 1.4.3 | Review design for manufacturability (including assembly) Review how product will be manufactured and how the key product functions will be protected and how the design affects manufacturability relating to risks.
|  | 1.4.4 | Identify risks and concerns and develop action plan- Conduct risk assessments to identify high/medium risk and define how the risk can be mitigated or reduced.
1.5 | APQP requirements / review checklist | 1.5.1 | APQP checklist with acceptance criteria- Review checklist to obtain agreement between supplier and TI Fluid Systems of which APQP elements (sub-elements) will be required and what the acceptance criteria will be.
|  | 1.5.2 | Establish target dates for each step (support milestones)- Dates must support TI Fluid Systems and OEM customer APQP timing and program Milestones.
1.6 | Equipment, tooling, gauges, and fixture design proposal and review | 1.6.1 | Review supplier equipment design concept- What equipment will be used? If new; how will it be acquired and how will it be qualified? When?
|  | 1.6.2 | Review supplier tooling design concept-What type of tooling will be used? Review key tool design features. How will it be acquired and how will it be qualified? When?
|  | 1.6.3 | Review supplier gauging design concept-What type of gauging will be used? Review key gauge design features. How will it be acquired and how will it be qualified? When? Will TIFS also require gauging? Is a correlation study required? How will this work?
|  | 1.6.4 | Review supplier check fixture design concept-What type of check fixture will be used? Review key fixture design features.how will it be acquired and how will it be qualified? When? Will TIFS also require a fixture? Is a correlation study required? How will this work?
1.7 | Production release process / scheduling concept | 1.7.1 | Review production release process- define how releases will be communicated, lead times, bottlenecks, how changes in schedule will be managed etc..
|  | 1.7.2 | Establish key contacts / escalation process- Assign key contacts at supplier and TI Fluid Systems and define the escalation process and who must be notified should problems occur relating to scheduling.
|  | 1.7.3 | Define scheduling- How will schedules be communicated between the supplier and TI Fluid Systems?
1.8 | Packaging / logistics concepts / inventory management | 1.8.1 | What is the supplier's concept of how the parts will be packaged? How will parts be shipped? What type of inventory controls will be utilized?
1.9 | Resources and training review | 1.9.1 | What resources will be required for this program? Does the supplier have to hire or add staff? Who will be responsible for training associates on this program? When will this be completed?
1.10 | Initiate APQP progress report and begin reporting | 1.10.1 | Initiate the APQP Progress Report at the conclusion of this meeting and agree to reporting schedule.
1.11 | Open issues document | 1.11.1 | Initiate the APQP Open Issues report at the conclusion of this meeting, set corrective action dates and agree to reporting schedule.
1.12 | Preliminary capacity study | 1.12.1 | Review supplier capacity against possible scheduling scenarios to ensure there is no risk. Also review planned downtime, annual maintenance schedules and any other impact on available manufacturing days to assure they are addressed in the capacity review.
1.13 | Manufacturing feasibility | 1.13.1 | Supplier presents their formal Manufacturing Feasibility Statement.
1.14 | Supplier presents proposed plan / timing (written) | 1.14.1 | Supplier develops formal APQP plan based on Milestone 1 definitions and submits the written plan to TI Fluid Systems for review.
1.15 | Confirm level of P.O. is correct at this point in APQP | 1.15.1 | Verify P.O. level and drawing is correct and any changes made to the P.O. have been communicated properly, agreed upon by the supplier and reflected in the APQP plan at this stage of the program.
1.16 | Milestone Review/ Sign Off | 1.16.1 | Formal review and sign-off of Supplier Milestone #1 by the TIFS Program Team

## Milestone 2
Milestone #2- "Tooling, Gauging and Equipment Design"
Minor Milestone | Minor Milestone Description | Detail | Detail Description | Supplier Plan | Due Date | Date Completed | Evidence Available Y/N
2.1 | DFMEA Review | 2.1.1 | Supplier DFMEA if they are responsible/ TI Fluid Systems DFMEA if TI Fluid Systems is responsible. Is it available?
|  | 2.1.2 | Technical review of DFMEA to verify all potential design failure modes have been identified and addressed. Confirm drawing level is correct. If the DFMEA is not correct, then why not?
|  | 2.1.3 | Verify AIAG guidelines were followed when developing the RPN values for this DFMEA or as otherwise agreed by TI Fluid Systems.
|  | 2.1.4 | Review any/all high RPN parameters for this DFMEA and discuss options to reduce the risk.
|  | 2.1.5 | Discuss and verify this DFMEA addresses manufacturability and assembly related risks regarding the design?
2.2 | Preliminary Process Flow, PFMEA and Control Plan review. | 2.2.1 | Preliminary Process Flow Diagram prepared by cross functional team and ready for review.
|  | 2.2.2 | Technical review of Preliminary Process Flow Diagram to ensure all process steps, handling and storage areas were included.
|  | 2.2.3 | PFMEA was prepared by cross functional team and available for review.
|  | 2.2.4 | Technical review of PFMEA to verify all potential process failure modes have been identified and addressed. Confirm drawing level is correct. If the PFMEA is not correct, then why not?
|  | 2.2.5 | Verify AIAG guidelines were followed when developing the RPN values for this PFMEA or as otherwise agreed by TI Fluid Systems.
|  | 2.2.6 | Review any/all high RPN parameters for this PFMEA and discuss options to reduce the risk.
|  | 2.2.7 | Discuss design and function related risks and verify they have been addressed in this PFMEA?
|  | 2.2.8 | Preliminary Process Control Plan was developed by cross functional team and is available for review.
|  | 2.2.9 | Technical review of the Preliminary Process Control Plan to ensure all parameters in the Process Flow Diagram are included and all controls from the PFMEA are included.
|  | 2.2.10 | Verify all APQP documents are matched and link together properly. (DFMEA, Process Flow Diagram, PFMEA and Control Plan)
2.3 | Subcontractor Plan and supplier list/ BOM | 2.3.1 | Review supplier BOM and subcontractor list for the program.
|  | 2.3.2 | Review supplier APQP and Launch Plan for subcontractors
|  | 2.3.3 | Review PPAP timing and requirements for subcontractors.
|  | 2.3.4 | Identify any subcontractors that pose a risk to the program and ensure corrective actions are taken.
2.4 | Formal review of supplier equipment, tooling, gauging and fixture plans. | 2.4.1 | Review supplier equipment concepts, drawings and proposed build schedule.
|  | 2.4.2 | Review supplier tooling concepts, drawings and proposed build schedule.
|  | 2.4.3 | Review supplier gauging concepts, drawings and proposed build schedule.
|  | 2.4.4 | Review supplier fixtures concepts, drawings and proposed build schedule.
|  | 2.4.5 | Review user plant gauging concepts, drawings and proposed build schedule and inspection criteria.
|  | 2.4.6 | Review user plant fixtures concepts, drawings and proposed build schedule and inspection criteria.
2.5 | Preliminary discussion regarding tool and equipment maintenance plans. | 2.5.1 | Supplier Preventative Maintenance plans for equipment, tooling, gauging and fixtures etc are prepared and available for review.
|  | 2.5.2 | Properly trained resources are available as required to support the required maintenance plans.
2.6 | Preliminary discussion for supplier contingency/ emergency plans. | 2.6.1 | Written "executable" contingency plans for equipment, tooling, gauging and fixtures meets TIFS requirements and is available for review.
|  | 2.6.2. | Supplier had written "executable" plan for emergency situations such as loss of power to the plant, loss of water, and any other concern that could cause unexpected downtime and potential threat to delivery.
2.7 | Confirm level of P.O. and drawing is correct at this point in APQP | 2.7.1 | Verify P.O. level and drawing is correct and any changes made to the P.O. have been communicated properly, agreed upon by the supplier and reflected in the APQP plan at this stage of the program.
2.8 | Milestone Review/ Sign Off | 2.8.1 | Formal review and sign-off of Supplier Milestone #2 by the TIFS Program Team

## Milestone 3
Milestone #3- "Product/Process Realization"
Minor Milestone | Minor Milestone Description | Detail | Detail Description | Supplier Plan | Due Date | Date Completed | Evidence Available Y/N
3.1 | Review production level Process Flow Diagram | 3.1.1 | Process Flow Diagram prepared by cross functional team and ready for review.
|  | 3.1.2 | Technical review of Process Flow Diagram to ensure all process steps, handling and storage areas were included. Verify any changes to the flow diagram since concept have been documented and all other APQP documents are updated and linked accordingly.
3.2 | Review production level plans for packaging, handling and storage. | 3.2.1 | Review written plans for packaging and plans for testing/qualification of the packaging. (Internal packaging and external)
|  | 3.2.2 | Review written plans for handling and plans for monitoring handling during production. (Layered Process Audits (LPA)? Or other internal audit?
|  | 3.2.3 | Review written plans for storage to ensure FIFO, proper protection of the product, elimination of risk for contamination, proper identification and lot control maintained, etc.
3.3 | Review supplier Early Production Containment (EPC) plans. | 3.3.1 | Written EPC plan defines additional controls, inspection audits, testing and other measures required to ensure high level of confidence of quality during the containment period.
|  | 3.3.2 | The EPC takes into account known quality concerns, all critical conditions, areas identified as potential risk items in the DFMEA and PFMEA.
|  | 3.3.3 | The EPC plan commences at SOP and not end until 90 days or until exit criteria as specified by TI Fluid Systems has been satisfied.
3.4 | Finalize process capability plan/ KPI's | 3.4.1 | Process Capability plan includes all SC/CC and KPI's as agreed upon between the supplier and TI Fluid Systems.
|  | 3.4.2 | The quantity/frequency of studies and the acceptance criteria for the PpK and CpK complies with the requirements agreed with TI Fluid Systems.
|  | 3.4.3 | Data/evidence will be provided to TI Fluid Systems at frequencies and in the format as agreed upon between the supplier and TI Fluid Systems.
3.5 | Review floor plan layout, process instructions, 5S plan, visual aides and other manufacturing measures. | 3.5.1 | Review floor plan layout including locations for processing, WIP, storage, receiving and shipping etc.
|  | 3.5.2 | Review Process Instructions and inspection instructions and verify how they will be communicated and trained to associates on the floor.
|  | 3.5.3 | Review 5S Plan, location and availability of Visual Aides and any other manufacturing displays or measures relevant to this project. Include discussion on how any changes to these documents will be managed.
3.6 | Verification review of "off tool" product and functionality of tool. | 3.6.1 | Run off tool samples to verify the tooling and equipment is functioning properly and that all safe guards, lock outs, etc are in place as needed. Must use production level materials and equipment/tooling.
|  | 3.6.2 | Review final PM plan for robustness, verify all appropriate spare parts/supplies are available and planned accordingly.
3.7 | Review of tooling, equipment and gauging status/ Trials and timing. | 3.7.1 | Review final plans for equipment, progress update, timing for trials and PSO, qualification and acceptance criteria and contingency plans.
|  | 3.7.2 | Review final plans for tooling, progress update, timing for trials and PSO, qualification and acceptance criteria and tool maintenance and contingency plans.
|  | 3.7.3 | Review final plans for gauges, progress update, timing for trials and MSA and gauge R&R studies, qualification and acceptance criteria and contingency plans.
3.8 | Review quality status of product | 3.8.1 | Evaluate quality status of product off tool and production level equipment, materials and processes.
|  | 3.8.2 | Identify any areas of concern for the quality of the product and develop action plan to correct these concerns prior to PPAP and SOP.
|  | 3.8.3 | Evaluate the quality status of sub-contractor products off production tooling and materials and identify any areas of concern for the quality of the product and develop action plan to correct these concerns prior to PPAP and SOP.
3.9 | Confirm level of P.O. is correct at this point in APQP | 3.9.1 | Verify P.O. level and drawing is correct and any changes made to the P.O. have been communicated properly, agreed upon by the supplier and reflected in the APQP plan at this stage of the program.
3.10 | Milestone Review/ Sign Off | 3.10.1 | Formal review and sign-off of Supplier Milestone #3 by the TIFS Program Team

## Milestone 4
Milestone #4- "Pre-PPAP and Launch Readiness"
Minor Milestone | Minor Milestone Description | Detail | Detail Description | Supplier Plan | Due Date | Date Completed | Evidence Available Y/N
4.1 | Pre-Production Run | 4.1.1 | Schedule Pre-Production Run/ Notify TI Fluid Systems of dates/timing.
|  | 4.1.2 | Verify the quantity and expected outcomes/results of the Pre-Production Run are in line with TI Fluid Systems requirements and all anticipated outcomes are confirmed.
|  | 4.1.3 | Collect data as agreed upon with TI Fluid Systems and prepare evidence and documents for review.
4.2 | Run at Rate (R@R) | 4.2.1 | Complete Run at Rate (R@R) per agreed upon guidelines and collect all data and records as required for documentation.
|  | 4.2.2 | Record any non-compliances, production concerns or any issues with equipment and tooling.
|  | 4.2.3 | Document any unplanned downtime and develop plan for prevention during production.
|  | 4.2.4 | Collect all scrap, rework etc and analyze for corrective action. Verify any/all scrap is reflected in the PFMEA as potential risk and adjust RPN values accordingly to reflect actual count.
4.3 | Verify production level packaging, handling and storage requirements have been met. | 4.3.1 | Verify evidence for packaging, labeling, handling, storage and packaging contingency.
4.4 | Production Sign Off (PSO) | 4.4.1 | Prepare all information as agreed upon for disposition of Production Sign Off (PSO)
|  | 4.4.2 | Review PSO results with TI Fluid Systems and present action plan for any concerns or potential risks identified during the trial runs.
4.5 | Process Capability Study | 4.5.1 | Collect and evaluate production parts and prepare Process Capability Studies as agreed upon by TI Fluid Systems.
|  | 4.5.2 | Provide evidence to TI Fluid Systems that all studies demonstrated control and capability as defined by TI Fluid Systems.
|  | 4.5.3 | The scope of the process controls, tests and inspections include continuous monitoring and must consistently ensure stability and capability of the individual processes.
4.6 | Finalize PFMEA and Control Plan | 4.6.1 | Production Level PFMEA was prepared by cross functional team and available for review.
|  | 4.6.2 | Technical review of PFMEA to verify all potential process failure modes have been identified and addressed. Verify all lessons learned from production trials has been captured and included. Verify any/all changes in process have been included. Confirm drawing level is correct. If the PFMEA is not correct, then why not?
|  | 4.6.3 | Verify AIAG guidelines were followed when developing the RPN values for this PFMEA or as otherwise agreed by TI Fluid Systems.
|  | 4.6.4 | Review any/all high RPN parameters for this PFMEA and discuss options to reduce the risk.
|  | 4.6.5 | Discuss any design changes and verify the function related risks and verify they have been addressed in this PFMEA?
|  | 4.6.6 | Production Level Process Control Plan was developed by cross functional team and is available for review.
|  | 4.6.7 | Technical review of the Preliminary Process Control Plan to ensure all parameters in the Process Flow Diagram are included and all controls from the Production Level PFMEA are included.
|  | 4.6.8 | Verify all Production Level APQP documents are matched and link together properly. (DFMEA, Process Flow Diagram, PFMEA and Control Plan)
|  | 4.6.9 | Define annual recertification requirements and tracking method for supplier.
4.7 | Measurement System Analysis (MSA)/ Gauge R&R | 4.7.1 | MSA/Gauge R&R studies were conducted to confirm/verify the test and measurement equipment used for production will enable defect-free parts.
|  | 4.7.2 | Gauge R&R values are within the acceptable levels as identified by TI Fluid Systems.
|  | 4.7.3 | Calibration and gauge maintenance plans are available for review.
4.8 | Material Performance | 4.8.1 | Supplier has evidence that any/all materials or sub-components fully comply with the specifications, industry or government regulations and standards.
|  | 4.8.2 | Supplier evidence includes test results and data prepared by properly approved and accredited laboratories.
4.9 | Complete TI Fluid Systems Supplier PPAP Checklist | 4.9.1 | Checklist has been completed and is ready for TI Fluid Systems review and disposition. All required items are included and all evidence is available as required by TI Fluid Systems.
4.10 | Review Key subcontractor information | 4.10.1 | Evidence is available for all sub-contractor products and supplier confirms all materials, sub-components and products used to produce the TI Fluid Systems product meets all requirements as defined by TI Fluid Systems.
4.11 | Verify PVP&R status and report | 4.11.1 | Verify plan was executed and met requirements as agreed upon with the supplier.
4.12 | Launch Readiness Review | 4.12.1 | Supplier has a written Launch Readiness plan that includes sub-contractor details as required.
|  | 4.12.2 | Supplier is prepared to support TI Fluid Systems for a safe and successful launch and has all the evidence as required available.
4.13 | Confirm level of P.O. is correct at this point in APQP | 4.13.1 | Verify P.O. level and drawing is correct and any changes made to the P.O. have been communicated properly, agreed upon by the supplier and reflected in the APQP plan at this stage of the program.
4.14 | Milestone Review/ Sign Off | 4.14.1 | Formal review and sign-off of Supplier Milestone #4 by the TIFS Program Team

## Milestone 5
Milestone #5- "Process/Product Validation, Launch & Review Lessons Learned"
Minor Milestone | Minor Milestone Description | Detail | Detail Description | Supplier Plan | Due Date | Date Completed | Evidence Available Y/N
5.1 | Supplier PPAP submission and approval | 5.1.1 | PPAP Submission/Disposition/All open issues closed. Revalidation date confirmed.
|  | 5.1.2 | If interim approval, commitment date for follow up PPAP submission.
5.2 | Confirmation of ramp plan/supply chain readiness | 5.2.1 | Verify ramp plans still match for supplier, customer and sub-contractors. NO issues with delivery exist.
|  | 5.2.2 | Contact information available and escalation/notification process agreed upon for any potential delivery problems during product/ product life cycle.
5.3 | Review of EPC data/evidence(ongoing) | 5.3.1 | Review final results of EPC and verify all acceptance criteria has been met to end the containment process. Submit evidence to TI Fluid Systems for disposition.
|  | 5.3.2 | Review EPC data to ensure any/all concerns have been documented and addressed accordingly in all relevant APQP documents.
|  | 5.3.4 | TI responds with disposition for EPC
5.4 | Review of final KPI's, EPC results, PPAP results and overall launch effectiveness | 5.4.1 | Final review of data, results and issues identified during EPC and verification all issues have been properly closed.
|  | 5.4.2 | Final review of data, results and issues regarding KPI's tracked during APQP process and verification all issues have been properly closed.
|  | 5.4.3 | Final review of data, results and issues identified during PPAP process and verification all issues have been properly closed.
|  | 5.4.4 | Review and summary of overall launch effectiveness including all metrics, containments and deliverables.
5.5 | Brainstorm and collect Lessons Learned for both the Supplier and TI Fluid Systems. | 5.5.1 | Schedule meetings between TI Fluid Systems and supplier to brainstorm the APQP process, all metrics and requirements to identify areas for improvement and best practices. Document Lessons Learned for the Supplier and for TI Fluid Systems.
5.6 | Issue final Launch Report | 5.6.1 | Issue final launch report and close the APQP process for the supplier.
5.7 | Confirm level of P.O. is correct at this point in APQP | 5.7.1 | Verify P.O. level and drawing is correct and any changes made to the P.O. have been communicated properly, agreed upon by the supplier and reflected in the APQP plan at this stage of the program.
5.8 | Milestone Review/ Sign Off | 5.8.1 | Formal review and sign-off of Supplier Milestone #5 by the TIFS Program Team

## Reason For Change Table
Document Number: | CF-8-ALL-4800 | Document Title: | APQP Checklist
Document Usage: | Supplier APQP Process | Document Scope: | Corporate / All Regions
Revision Letter | Revision Date | Document Changes | Approval History
A | 14th of June 2011 | Implementation of the Corporate template to support the Supplier APQP process | D. Butler*
B | 2018-02-12 | Number change to align with IATF 16949. | Global Director Corporate Quality Systems
C | 2nd June 2021 | Update Logo multiple locations TI Fluid Systems / TIFS was TI Automotive / TI multiple locations Format milestone charts Include coversheet. | Corporate Quality Systems Director